## Sheet1
Sydney Airbnb Data Analysis Tool Project
Task ID | Task | Duration (Weeks) | Start Date | End Date
1 | Gather Requirements | 5 | 2023-08-21 | 2023-09-25
2 | Define Tool's Objectives | 2 | 2023-09-01 | 2023-09-15
3 | Create project plan | 4 | 2023-09-15 | 2023-10-13
4 | Allocate Resources | 3 | 2023-10-09 | 2023-10-30
5 | Set Deadlines and Milestones | 3 | 2023-10-20 | 2023-11-10
6 | Designing Sample for User Interface | 3 | 2023-11-09 | 2023-11-30
7 | Dvelopers write Source Code | 6 | 2023-11-22 | 2024-01-03
8 | Modules Addition to Code | 5 | 2023-12-02 | 2024-01-06
9 | Integration Testing | 4 | 2023-12-18 | 2024-01-15
10 | Test Planning | 3 | 2024-01-01 | 2024-01-22
11 | Test Execution | 6 | 2024-01-20 | 2024-03-02
12 | Test Reporting and Defect Management | 4 | 2024-02-14 | 2024-03-13
13 | Test Closure | 2 | 2024-02-21 | 2024-03-06
14 | Program Release | 4 | 2024-03-01 | 2024-03-29
15 | Program Deployment | 3 | 2024-03-19 | 2024-04-09
16 | Program Maintenance | 5 | 2024-03-01 | 2024-04-09
35
14
28
21
21
21
42
35
28
21
42
28
14
28
21
39
Formulas:
Start Date = [End Date, row above]